## 1__Guidance_&_Instructions
Construction Works and Associated Services
RM6088

Key Performance Indicators - Additional Client Call Off Projects

Introduction

This template is designed to support the Additional Client in assessing and measuring performance of the Supplier Alliance Member in delivery of Project requirements through the use of framework RM6088 - Construction Works & Associated Services
The KPI model is made up of common industry measures designed to assess performance in a fair and transparent manner, measuring aspects of project delivery and project specific measures. These measures can be refined and adjusted as required and aligned to project specific measures.
The KPI measures set out focus on criteria linked to project delivery, timings, costs, quality and Health & Safety, which are commonly identified as essential areas that enable projects to be delivered successfully.
Bespoke KPIs enable the Additional Client to develop further performance metrics to ensure project specific requirements and special areas of performance are considered and measured.

This document is intended to be completed by the Additional Client and/or the Supplier Alliance member following regular feedback on a an agreed time frequency, to be agreed at point of call off.
Scoring approach and scoring rationale can be agreed between the Additional Client and Supplier Alliance Memeber on a project by project basis.
Some areas that may be considered in addition to the set KPIs in this template could include: Productivity, Building Information Modelling, Social Value, Inclusivity & Diversity, Client Satisfaction, Carbon Reduction etc.

A suggested baseline has been included against each KPI measure for information purposes only, linked to common criteria outputs and potential delivery levels. Expectations will differ on a project by project basis so it is advised that any baseline measures utilised at call off stage are reflective of the project specific requirements and required performance levels.
Additional KPI measures can be developed and included within the template that may cover specialist requirements linked to performance.

It is the responsibility of the Additional Client to agree levels of performance and frequency of recording KPI performance with each Supplier Alliance Member. Early agreement of KPIs is recommended to enable performance against project requirements to commence from the earliest possible stage of a project.
Incentivisation and/or Pain/Gain share mechanisms can be applied to the KPI model and mechanisms applied linked to performance.. This will need to be addressed by the Additional Client and based on project specific requirements addressed at call off stage.

## 2__KPI_Scoring_Model
			Construction Works & Associated Services / Key Performance Indicators

		KPI Used	KPI Owner (if applicable)	KPI Measure	Purpose	Performance Measure	Typical Baseline Example	Actual Baseline Adopted (insert number only)
	Project Delivery Measurement / Safety Compliance and Performance			Number of hazards identified in the month	It has been demonstrated that increasing the number of hazards identified leads to a greater number of accidents being prevented	Number of Hazards identified during the month / Number of operative weeks worked during the month	1
				Number of hours worked since the last "RIDDOR Incident"	Measure of safe working performance	Total site hours worked since last RIDDOR Incident or over 3 day incapacitation / Total site hours worked	1
				Accident Frequency Rate	Measure of safe working performance	AFR = No. of lost time accidents x 100,000 / No of man hours worked	0

		KPI Used	KPI Owner (if applicable)	KPI Measure	Purpose	Performance Measure	Typical Baseline Example	Actual Baseline Adopted (insert number only)
	Project Delivery Measurement / TIME			Project Planning	Regular provision and agreement of contract programme has been shown to lead to more predictable outcome of completion date.	Number of months an updated programme has been agreed / the number of months since project commencement. A score below 1 is below the required and expected performance level.	1
				Time Predictability	This measure focuses on behavioural performance measuring how reasonable the contractor is in initial claimed Extensions of Time	Total Contractor initial estimated Extensions of Time / total agreed Extensions of Time	1
				Early Warnings (1) Quantity of Early Warnings issued to the client that are prior to an event occurring during project delivery	Early shared visibility of issues has been shown to improve contract performance. Issue prior to the event allows full range of mitigation measures to be applied.	Number of early warnings issued prior to event occurring / Number of early warnings issued after the event occurring	1
				Early Warnings (2) - Time taken, on average, between agreeing action from Early Warning event occurring	The sooner that a mitigation is agreed, the better the outcome for the Additional Client and project	Average time taken to agree mitigation action following submission of an early warning(s)	21 Days (Subject to specific form of contract)

		KPI Used	KPI Owner (if applicable)	KPI Measure	Purpose	Performance Measure	Typical Baseline Example	Actual Baseline Adopted (insert number only)
	Project Delivery Measurement / Cost			Cost Predictability	Accurate early cost forecasting by Contractor indicates positive and collaborative commercial behaviour	Contractor initial claimed cost of change/agreed cost of change	1
				Average time to agree time and cost impact of change	Additional costs agreed as soon as possible after the change event, have been shown to be more accurate and allow for better final cost forecasting	Average time taken to agree cost of changes following issue of variation instructions	60 days
				Growth	Measures degree of unanticipated change and associated cost growth	Forecast out-turn cost / initial contract sum	10%

		KPI Used	KPI Owner (if applicable)	KPI Measure	Purpose	Performance Measure	Typical Baseline Example	Actual Baseline Adopted (insert number only)
	Project Delivery Measurement / Quality			Number of defect notices issued	Number of defects notices identified and Issued in relation to project or programme	Number of defects notices identified and Issued in relation to project or programme	0
				Average time to correct notified defect	This drives compliance with contract requirements to rectify defects within set timescales.	Percentage of notified defects rectified within the contract timescale	100%
				Proportion of subcontracts approved by the Additional Client before award of work package	To allow the Additional Client input into the subcontractor procurement process prior to final selection decision for key agreed subcontract packages	Percentage of work packages approved before award	100%

		KPI Used	KPI Owner (if applicable)	KPI Measure	Purpose	Performance Measure	Typical Baseline Example	Actual Baseline Adopted (insert number only)
	Bespoke - Project Specific Measures			E.G. Productivity, Inclusivity & Diversity, Social Value, Client Satisfaction, Carbon Reduction

Yes
No