## Action_Plan
RM6130 ACTION PLAN TEMPLATE
Step	Task	Action	Progress	Comments	Links
1	Download action plan and document tracker	Download action plan	100%	N/A	N/A
		Review action plan and add or remove tasks as needed	10%	N/A	N/A
		Review the document tracker tab	0%	See the Document Tracker in the next sheet to familiarise yourself.	N/A
2	Create timeline	Create a procurement timeline	0%	Estimate how long each step of your procurement will take and work backwards from your proposed contract start date. / Decide whether you would like to host a site visit for suppliers to help them bid. / See Attachment 1 - About the Procurement in the Bid Pack Templates on RM6130 CCS webpage for a template timeline.	RM6130 CCS webpage
3	Complete Customer User Agreement (CUA)	Complete document and submit to CCS	0%	See Documents section on RM6130 CCS webpage	RM6130 CCS webpage
4	Gain internal approvals (if applicable)	Secure budget approval, procurement strategy approval and other relevant approvals	0%	N/A
5	Cabinet Office controls process	Check if Cabinet Office controls apply to this procurement	0%	The spend controls apply to all organisations classified as central government by the Office of National Statistics (ONS), with some exceptions. / See the Cabinet Office controls website for more information.	Cabinet Office Controls website
		(If applicable) Review Cabinet Office controls process and add its tasks to this list	0%	For full guidance on controls that relate to cleaning contracts, visit the Facilities Management Controls section of the website.	FM Controls section
6	Download RM6130 Bid Pack Templates	Download and save own versions of the Bid Pack Templates	0%	See Bid Pack Templates on RM6130 CCS webpage	RM6130 CCS webpage
7	Complete 'Attachment 3 – Requirements Specification'	Complete document	0%	This is the main document that tells suppliers the who, what, where, when, why and how of the service that you require. It also can form part of your contract. Your quality questions will be based on the information provided in this document.	RM6130 CCS webpage
		Decide on the KPIs to be used to manage the contract	0%	N/A	N/A
		Review final version prior to publication	0%	N/A	N/A
8	Complete appendices to 'Attachment 3 – Requirements Specification'	Create and include relevant appendices	0%	N/A	N/A
		Check all references to appendices are correct in the documentation	0%	N/A	N/A
9	Request and review TUPE information from previous supplier (if applicable)	Request TUPE information from previous supplier	0%	N/A	N/A
		Review received TUPE information	0%	N/A	N/A
10	Complete 'Attachment 1 – About this Procurement'	Complete document	0%	N/A	N/A
		Decide on contract length and any optional extensions	0%	N/A	N/A
		Review final version prior to publication	0%	N/A	N/A
11	Complete 'Attachment 2 – How to Bid'	Complete document	0%	N/A	N/A
		Decide on evaluation criteria (price and quality percentage weightings)	0%	N/A	N/A
		Decide on quality questions to be answered by suppliers and scored in evaluation	0%	N/A	N/A
		Review final version prior to publication	0%	N/A	N/A
12	Complete Pricing Matrix	Create Pricing Matrix for suppliers to submit their prices	0%	N/A	N/A
		Review final version prior to publication	0%	N/A	N/A
		'Lock' cells and 'protect' Excel workbook prior to publication	0%	N/A	N/A
13	Complete Terms and Conditions	Download Terms and Conditions	0%	They are found in the Documents section on the CCS RM6130 website	N/A
		Decide which Terms and Conditions to use for this procurement	0%	Use the Document Tracker in the next sheet	RM6130 CCS webpage
		Amend DPS Schedules	0%	These are all mandatory Schedules	N/A
		Amend DPS Joint Schedules	0%	Some of these Schedules are optional	N/A
		Amend DPS Order Schedules	0%	Some of these Schedules are optional	N/A
14	Download supplier list	Register to access DPS Marketplace system	0%	Access the system as a buyer	N/A
		Decide on most appropriate service and location filters for this procurement	0%	N/A	Access the system
		Run DPS filters and export supplier list (use within 2 working days)	0%	N/A	N/A
15	Decide on which online procurement tool to use	Decide which online procurement tool to use	0%	N/A	N/A
		Register to access CCS's eSourcing procurement tool (optional)	0%	N/A	N/A
		Finalise and gather all tender documentation, and name all documents accordingly	0%	For example: Attachment 4, Attachment 5, Appendix 1	N/A
		Build procurement in online procurement tool	0%	N/A	N/A
16	Send out Capability Assessment (optional)	Complete document with key requirements to refine shortlist	0%	N/A	N/A
		Send Capability Assessment to supplier list via online procurement tool	0%	See Bid Pack Templates on RM6130 CCS webpage	N/A
		Review submitted Capability Assessments and shortlist accordingly	0%	N/A	RM6130 CCS webpage
17	Publish tender	Invite suppliers to tender via online procurement tool	0%	N/A
		Respond to clarification questions via online procurement tool	0%	N/A	N/A
		Decide on evaluation team (who will evaluate the tenders?)	0%	At least 3 suitably experienced and qualified evaluators are usually chosen. Separate individual(s) should be chosen to evaluate price.	N/A
		Book time in evaluators' diaries for evaluating tenders and for moderation	0%	N/A	N/A
18	Organise site visits (optional)	Organise with suppliers when they can visit your premises in order to help them bid	0%	Make sure you share the same information with all suppliers throughout this stage, to ensure the competition remains fair.	N/A
19	Evaluate tender responses	At the tender response deadline, download tender responses from online procurement tool and send to evaluators	0%	N/A	N/A
		Evaluate tender responses	0%	N/A	N/A
		Moderate tender responses and decide on winning bid	0%	N/A	N/A
20	Internal governance (If applicable)	Submit the decision to award contract for internal approval	0%	N/A	N/A
		Receive and log approval	0%	N/A	N/A
21	Send outcome letters	Draft outcome letters to all suppliers that submitted a bid	0%	Include constructive feedback to all suppliers who bid, including a full breakdown of their score, and a comparison to the score of the winning supplier. There are template outcome letters on the RM6130 CCS webpage.	N/A
		Send outcome letters to all suppliers	0%	N/A	RM6130 CCS webpage
22	Complete supplier due diligence (if applicable)	Ask winning supplier for evidence of information mentioned in their bid	0%	N/A	N/A
		Ask winning supplier for evidence of information provided to be appointed onto the cleaning DPS e.g. contract example, Cyber Essentials certificate, insurance	0%	You can log-in to the DPS system and navigate to the supplier search you used for this procurement. Find the supplier(s) you wish to see further information for and click on the Request evidence button. The suppliers will then be sent a notification and will give you access to see the evidence.	N/A
		Complete supplier due diligence checks e.g. financial, references	0%	N/A	DPS system
		Review evidence and confirm decision to award contract to winning supplier	0%	N/A	N/A
23	Complete Order Schedules	Complete Order Schedules	0%	Use the Document Tracker in the next sheet to keep track.	N/A
24	Complete Order Form	Confirm contract start date with supplier	0%	N/A	N/A
		Complete 'DPS Schedule 6 - Order Form'	0%	N/A	N/A
		Sign Order Form (contract) with supplier	0%	N/A	N/A
25	Inform CCS	Inform CCS of the contract award	0%	Complete the Contract Award Notification letter on the RM6130 CCS website and send to info@crowncommercial.gov.uk	N/A
26	Publish details on Find a Tender service (if applicable)	Publish contract details on Contracts Finder/Find a Tender website	0%	N/A	N/A
27	Implementation/Mobilisation	Manage implementation of the new service with the new and incumbent supplier	0%	N/A	N/A

	If you need any help or have any questions about the RM6130 Building Cleaning Services agreement, contact info@crowncommercial.gov.uk (Quote RM6130)

## Document_Tracker
RM6130 Document Tracker
Document Title	Required?	Include?	Progress	Comments
Further Competition
Attachment 1 - About the Procurement	Yes	Yes	0%	This document give suppliers the core information about your procurement.
Attachment 2 - How to Bid	Yes	Yes	0%	This document tells suppliers how they should bid, including which online procurement tool you will use.
Attachment 3 - Requirements Specification	Yes	Yes	0%	This is the main document that tells suppliers the who, what, where, when, why and how of the service that you require. It also can form part of your contract. Your Quality Questions will be based on the information provided in this document.
Attachment 4 - Core Terms & Schedules (including Order Form)	Yes	Yes	0%	Once you have chosen and completed the relevant Schedules listed below that apply to your procurement, save them all in a ZIP folder named "Attachment 4 - Core Terms & Schedules (including Order Form)".
Attachment 5 - Pricing Matrix	Yes	Yes	0%	This is the spreadsheet that bidding suppliers will use to input their proposed prices. You can structure your pricing model however is best for your contract.
Attachment 6 - TUPE Information	If applicable	If applicable	0%	Ask your existing supplier to complete this template. Applies to all procurements where there is an existing supplier delivering the current service.
Terms and Conditions (DPS Schedules)
DPS Appointment Form v1 (Sample)	Mandatory	Yes	100%	Example supplier Appointment Form.
DPS Core Terms v1	Mandatory	Yes	100%	CCS's core terms.
DPS Schedule 1 - Specification	Mandatory	Yes	100%	The specification of the services that suppliers need to meet.
DPS Schedule 2 - DPS Application	Mandatory	Yes	100%	The application questions that suppliers complete to join the RM6130 DPS.
DPS Schedule 3 - DPS Pricing	Mandatory	Yes	100%	Details how DPS pricing works and the limits imposed on charges from suppliers.
DPS Schedule 4 - DPS Management	Mandatory	Yes	100%	Details how the DPS is managed by CCS.
DPS Schedule 5 - Management Levy and Information	Mandatory	Yes	100%	Details the Management Levy and information.
DPS Schedule 6 - Order Form Template and Order Schedules	Mandatory	Yes	0%	This is the Order Contract - a key document. To be completed as much as possible pre-tender and finalised at contract award.
DPS Schedule 7 - Order Procedure	Mandatory	Yes	0%	Input your award criteria in the annex - this should mirror the information in Attachment 2 - How to Bid.
DPS Schedule 8 - Self Audit Certificate	Mandatory	Yes	100%	A form used by CCS to audit suppliers.
DPS Schedule 9 - Cyber Essentials Scheme	Mandatory	Yes	100%	Details the requirements of suppliers to have a Cyber Essentials certificate.
Terms and Conditions (Joint Schedules)
DPS Joint Schedule 1 - Definitions	Mandatory	Yes	100%	Details the definitions of terms used in the Schedules.
DPS Joint Schedule 2 - Variation Form	Mandatory	Yes	100%	If you or your supplier would like to change any Schedules during the contract, this is the document to complete - both parties need to agree.
DPS Joint Schedule 3 - Insurance Requirements	Mandatory	Yes	100%	Details the minimum insurance requirements of suppliers.
DPS Joint Schedule 4 - Commercially Sensitive Information	Mandatory	Yes	0%	To be completed after contract award.
DPS Joint Schedule 5 - Corporate Social Responsibility	Mandatory	Yes	100%	Details the corporate social responsibilities of suppliers.
DPS Joint Schedule 6 - Key Subcontractors	If applicable	If applicable	100%	Details the process the supplier shall follow to change sub-contractors during the contract.
DPS Joint Schedule 7 - Financial Difficulties	If applicable	If applicable	100%	Details what shall happen if the supplier's financial risk score changes or if the supplier goes into financial distress.
DPS Joint Schedule 8 - Guarantee	If applicable	If applicable	0%	To be completed after contract award if applicable.
DPS Joint Schedule 9 - Minimum Standards of Reliability	If applicable	If applicable	100%	Outlines that suppliers must show that they meet certain minimum standards of reliability if the anticipated contract value is over £20 million (excluding VAT).
DPS Joint Schedule 10 - Rectification Plan	Mandatory	Yes	100%	During the contract, this form can be completed if the supplier encounters an issue that needs formally rectifying.
DPS Joint Schedule 11 - Processing Data	Mandatory	Yes	0%	To be completed as much as possible pre-tender and finalised at contract award.
DPS Joint Schedule 12 - Supply Chain Visibility	Mandatory	Yes	100%	Details the responsibilities of the supplier to ensure supply chain visibility.
Terms and Conditions (Order Schedules)
DPS Order Schedule 1 - Transparency Reports	Mandatory	Yes	0%	Applies to all Central Government Departments, their Executive Agencies and Non Departmental Public Bodies. It concerns the publication of procurement and contracts information to be disclosed to the public.
DPS Order Schedule 2 - Staff Transfer	Mandatory	Yes	0%	Concerns TUPE and staff transferring into and out of the contract.
DPS Order Schedule 3 - Continuous Improvement	Mandatory	Yes	100%	Details the supplier's responsibilities regarding continuous improvement.
DPS Order Schedule 4 - Order Tender	If applicable	If applicable	0%	To complete after contract award. Copy the winning supplier's tender response into this Schedule.
DPS Order Schedule 5 - Pricing Details	If applicable	If applicable	0%	To complete after contract award. Copy the winning supplier's Pricing Matrix into this Schedule.
DPS Order Schedule 7 - Key Supplier Staff	If applicable	If applicable	0%	To be completed after contract award. Supplier to detail the key members of its staff to work on the contract.
DPS Order Schedule 8 - Business Continuity and Disaster Recovery	If applicable	If applicable	100%	Applies if you require the supplier to have Business Continuity and Disaster Recovery plans.
DPS Order Schedule 9 - Security	If applicable	If applicable	0%	Choose the level of security requirements for the contract.
DPS Order Schedule 10 - Exit Management	If applicable	If applicable	0%	Details the supplier's exit management responsibilities.
DPS Order Schedule 11 - Installation Works	If applicable	If applicable	100%	Applies if you require the supplier to install anything during the contract.
DPS Order Schedule 12 - Clustering	If applicable	If applicable	0%	Applies if you are procuring services as part of a cluster of organisations.
DPS Order Schedule 13 - Implementation Plan and Testing	If applicable	If applicable	0%	Provides details around the implementation/mobilisation of the contract.
DPS Order Schedule 14 - Service Levels	If applicable	If applicable	0%	Contains your chosen KPIs/service levels for this contract. If you detail your Service Levels in the Requirements Specification, duplicate them here. If you only include your Service Levels in this Schedule, refer to this Schedule in your Requirements Specification.
DPS Order Schedule 15 - Order Contract Management	If applicable	If applicable	0%	Provides details around contract management responsibilities.
DPS Order Schedule 16 - Benchmarking	If applicable	If applicable	100%	Applies if you require the supplier to cooperate in a benchmarking exercise no less than every 12 months, to determine if the contract provides good value. Benchmarking exercise are at the cost of the Buyer.
DPS Order Schedule 17 - MoD Terms	If applicable	If applicable	0%	Applies to Ministry of Defence (MoD) procurements only.
DPS Order Schedule 18 - Background Checks	If applicable	If applicable	0%	Details the Relevant Convictions that shall exclude people from working on the contract.
DPS Order Schedule 19 - Scottish Law	If applicable	If applicable	0%	Applies if you wish the contract to be governed under Scottish law.
DPS Order Schedule 20 - Specification	If applicable	If applicable	0%	Copy over your "Attachment 3 - Requirements Specification" (once it is finalised), so that it forms part of the contract.
DPS Order Schedule 21 - Northern Ireland Law	If applicable	If applicable	100%	Applies if you wish the contract to be governed under Northern Ireland law.
DPS Order Schedule 22 - Lease Terms v.1.0	If applicable	If applicable	0%	Applies if you are going to be leasing equipment.
DPS Order Schedule 23 - Secret Matters v1.0	If applicable	If applicable	100%	Applies if the supplier will have access to secret information.