## procurement_timetable_for_2022
Procurement timetable for 2022 for RM6178 framework
This worksheet contains 4 timetables for the four procurement cycles of the year
The following table is for January 2022, with award deadline of 02/06/2022
Action+C18B5A4:C17A4:C19A4:CA4:D21	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 27th November 2021	Customer
Aggregate Customer switching-templates into one Master document	01/10/2021 > 06/12/2021	CAM
Build ITT pack	06/12/2021 > 11/12/2021	CAM / PO
Issue ITT pack	13/12/2021	PO
Respond to Clarifications by	02/01/2022	PO / CAM
ITT closes	04/01/2022	PO
Evaluate responses	05/01/2022 > 07/01/2022	PO
Issue invitation to eAuction	08/01/2022 > 09/01/2022	PO
Handover to eAuction team	08/01/2022 > 09/01/2022	PO
eAuction Training	12/01/2022	eAuction Team
eAuction	13/01/2022	eAuction Team
eAuction (rollover)	14/01/2022	eAuction Team
eAuction evaluation	15/01/2022	eAuction Team
Create report for Category	18/01/2022	eAuction Team
Issue award notification to suppliers	18/01/2022	PO
Create Customer award templates	19/01/2022	CAM
Issue award notification to customers	22/01/2022	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	22/01/2022 > 2/02/2022	Customer
Contract Commences	22/01/2022 + 90 Working days
The following table is for April 2022, with award deadline of 01/09/2022
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 25th February 2022	Customer
Aggregate Customer switching-templates into one Master document	28/02/2022 > 04/03/2022	CAM
Build ITT pack	07/03/2022 > 11/03/2022	CAM / PO
Issue ITT pack	11/3/2022	PO
Respond to Clarifications by	24/03/2022	PO / CAM
ITT closes	26/03/2022	PO
Evaluate responses	29/03/2022 > 31/03/2022	PO
Issue invitation to eAuction	04/04/2022 > 05/04/2022	PO
Handover to eAuction team	04/04/2022 > 05/04/2022	PO
eAuction Training	06/04/2022	eAuction Team
eAuction	07/04/2022	eAuction Team
eAuction (rollover)	08/04/2022	eAuction Team
eAuction evaluation	10/04/2022	eAuction Team
Create report for Category	21/04/2022	eAuction Team
Issue award notification to suppliers	21/04/2022	PO
Create Customer award templates	22/04/2022	CAM
Issue award notification to customers	26/04/2022	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	26/04/2022 > 10/05/2022	Customer
Contract Commences	26/04/2022 + 90 Working days
The following table is for October 2022, with award deadline of 30/11/2022
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 20th May 2022	Customer
Aggregate Customer switching-templates into one Master Switching-template	23/05/2022 > 27/05/2022	CAM
Build ITT pack	30/05/2022 > 07/06/2022	CAM / PO
Issue ITT pack	07/06/2022	PO
Respond to Clarifications by	14/06/2022	PO / CAM
ITT closes	20/06/2022	PO
Evaluate responses	20/06/2022 > 24/06/2022	PO
Issue invitation to eAuction	29/06/2022 > 30/06/2022	PO
Handover to eAuction team	04/07/2022 > 07/07/2022	PO
eAuction Training	08/07/2022	eAuction Team
eAuction	12/07/2022	eAuction Team
eAuction (rollover)	13/07/2022	eAuction Team
eAuction evaluation	15/07/2022	eAuction Team
Create report for Category	22/07/2022	eAuction Team
Issue award notification to suppliers	22/07/2022	PO
Create Customer award templates	22/07/2022	CAM
Issue award notification to customers	27/07/2022	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	27/07/2022 > 19/08/2022	Customer
Contract Commences	27/07/2022 + 90 working days
The following timetable is for October 2022, with the award deadline of 02/03/2023
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 26th August 2022	Customer
Aggregate Customer switching-templates into one Master document	30/08/2022 > 05/09/2022	CAM
Build ITT pack	05/09/2022 > 09/09/2022	CAM / PO
Issue ITT pack	09/09/2022	PO
Respond to Clarifications by	22/09/2022	PO / CAM
ITT closes	26/09/2022	PO
Evaluate responses	27/09/2022 > 29/09/2022	PO
Issue invitation to eAuction	03/10/2022 > 04/10/2022	PO
Handover to eAuction team	03/10/2022 > 04/10/2022	PO
eAuction Training	05/10/2022	eAuction Team
eAuction	06/10/2022	eAuction Team
eAuction (rollover)	07/10/2022	eAuction Team
eAuction evaluation	10/10/2022	eAuction Team
Create report for Category	20/10/2022	eAuction Team
Issue award notification to suppliers	20/10/2022	PO
Create Customer award templates	21/10/2022	CAM
Issue award notification to customers	25/10/2022	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	25/10/2022 > 08/11/2022	Customer
Contract Commences	25/10/2022 + 90 working days