## Procurement_timetable_for_2024
Procurement timetable for 2024 for RM6178 framework
This worksheet contains 4 timetables for the four procurement cycles of the year
the following table is for January 2024, with award deadline of 04/06/2024
Action	Completion date	Action owner
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 24th November 2023	Customer
Aggregate Customer switching-templates into one Master document	27/11/2023 > 01/12/2023	CAM
Build ITT pack	04/12/2023 > 08/12/2023	CAM / PO
Issue ITT pack	08/12/2023	PO
Respond to Clarifications by	02/01/2024	PO / CAM
ITT closes	04/01/2024	PO
Evaluate responses	08/01/2024 > 10/01/2024	PO
Issue invitation to eAuction	10/01/2024 > 11/01/2024	PO
Handover to eAuction team	10/01/2024 > 11/01/2024	PO
eAuction Training	15/01/2024	eAuction Team
eAuction	16/01/2024	eAuction Team
eAuction (rollover)	17/01/2024	eAuction Team
eAuction evaluation	18/01/2024	eAuction Team
Create report for Category	19/01/2024	eAuction Team
Issue award notification to suppliers	19/01/2024	PO
Create Customer award templates	22/01/2024	CAM
Issue award notification to customers	24/01/2024	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	24/01/2024 > 5/02/2024	Customer
Contract Commences	24/01/2024 + 90 Working days

The following table is for April 2024, Award deadline 01/09/2024
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 26th February 2024	Customer
Aggregate Customer switching-templates into one Master document	04/03/2020 > 08/03/2024	CAM
Build ITT pack	11/03/2024 > 15/03/2024	CAM / PO
Issue ITT pack	15/3/2024	PO
Respond to Clarifications by	18/03/2024	PO / CAM
ITT closes	20/03/2024	PO
Evaluate responses	25/03/2024 > 28/03/2024	PO
Issue invitation to eAuction	02/04/2024 > 03/04/2024	PO
Handover to eAuction team	02/04/2024 > 03/04/2024	PO
eAuction Training	08/04/2024	eAuction Team
eAuction	09/04/2024	eAuction Team
eAuction (rollover)	10/04/2024	eAuction Team
eAuction evaluation	11/04/2024	eAuction Team
Create report for Category	15/04/2024	eAuction Team
Issue award notification to suppliers	19/04/2024	PO
Create Customer award templates	22/04/2024	CAM
Issue award notification to customers	26/04/2024	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	26/04/2024 > 10/05/2024	Customer
Contract Commences	26/04/2024 + 90 Working days
The following table is for July 2024, award deadline 02/12/2024
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 24th May 2024	Customer
Aggregate Customer switching-templates into one Master Switching-template	28/05/2024 > 31/05/2024	CAM
Build ITT pack	03/06/2024 > 07/06/2024	CAM / PO
Issue ITT pack	07/06/2024	PO
Respond to Clarifications by	17/06/2024	PO / CAM
ITT closes	20/06/2024	PO
Evaluate responses	24/06/2024 > 28/06/2024	PO
Issue invitation to eAuction	01/07/2024 > 02/07/2024	PO
Handover to eAuction team	3/07/2024 > 04/07/2024	PO
eAuction Training	08/07/2024	eAuction Team
eAuction	09/07/2024	eAuction Team
eAuction (rollover)	10/07/2024	eAuction Team
eAuction evaluation	11/07/2024	eAuction Team
Create report for Category	22/07/2024	eAuction Team
Issue award notification to suppliers	22/07/2024	PO
Create Customer award templates	23/07/2024	CAM
Issue award notification to customers	29/07/2024	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	29/07/2024 > 19/08/2024	Customer
Contract Commences	29/07/2024 + 90 working days
The following table is for October 2024, with award deadline of 02/03/2025
Action	Completion Date:	Action Owner:
Customers send completed switching template to CCS / (FINAL DEADLINE) / Please note that incomplete templates will be returned and excluded from the competition to ensure the process is not delayed.	Friday 30th August 2024	Customer
Aggregate Customer switching-templates into one Master document	02/09/2024 > 06/09/2024	CAM
Build ITT pack	09/09/2024 > 13/09/2024	CAM / PO
Issue ITT pack	13/09/2024	PO
Respond to Clarifications by	23/09/2024	PO / CAM
ITT closes	24/09/2024	PO
Evaluate responses	30/09/2024 > 02/10/2024	PO
Issue invitation to eAuction	03/10/2024 > 04/10/2024	PO
Handover to eAuction team	03/10/2024 > 04/10/2024	PO
eAuction Training	07/10/2024	eAuction Team
eAuction	08/10/2024	eAuction Team
eAuction (rollover)	09/10/2024	eAuction Team
eAuction evaluation	10/10/2024	eAuction Team
Create report for Category	21/10/2024	eAuction Team
Issue award notification to suppliers	21/10/2024	PO
Create Customer award templates	22/10/2024	CAM
Issue award notification to customers	25/10/2024	CAM
Customer to complete Short Form Contract and send to Supplier for final sign-of. / The supplier will countersign and return the completed call-off contract back to CCS:	25/10/2024 > 08/09/2024	Customer
Contract Commences	25/10/2024 + 90 working days