## Action Plan
All documents can be found under the 'Documents' tab on the RM6264 web page: https://www.crowncommercial.gov.uk/agreements/RM6264
Task Title/Document | Task | Progress | Comments
Action Plan & Document Tracker | Download Action Plan | 100%
| Review Action Plan and add/remove tasks as appropriate | 10%
| Review Document Tracker | 0% | See the Document Tracker in the next sheet to familiarise yourself.
Timeline | Create procurement timeline/project plan | 0% | Estimate how long each part of your procurement will take, and work backwards from your proposed contract start date. Decide whether you would like to host a site visit for suppliers to help them bid. See 'Attachment 1 - About the Procurement' the RM6264 CCS webpage for a template timeline.
Customer User Agreement | Complete document and submit to CCS | 0% | See 'Documents' section on RM6264 CCS webpage
Internal approvals (if applicable) | Secure budget approval, procurement strategy approval and other relevant approvals | 0%
Cabinet Office Controls | Check if Cabinet Office Controls apply to this procurement | 0% | The spend controls apply to all organisations classified as central government by the Office of National Statistics (ONS), with some exceptions. See the Cabinet Office Controls website for more information. Full guidance on controls that relate to cleaning contracts, visit the FM Controls section of the website. | Cabinet Office Controls website | FM Controls section
| (If applicable) Review Cabinet Office Controls process and add its tasks to this list | 0%
RM6264 Bid Pack | Download from website and save own versions | 0% | See on RM6264 CCS webpage
Attachment 3 – Requirements Specification | Complete document | 0% | This is the main document that tells suppliers the who, what, where, when, why and how of the service that you require. It also can form part of your contract. Your Quality Questions will be based on the information provided in this document.
| Decide on KPIs to be used to manage contract | 0%
| Review final version prior to publication | 0%
Appendices to 'Attachment 3 – Requirements Specification' | Create and include relevant appendices | 0%
| Check all references to appendices are correct in the documentation | 0%
TUPE information from previous supplier (if applicable) | Request TUPE information from previous supplier | 0%
| Review received TUPE information | 0%
Attachment 1 – About this Procurement | Complete document | 0%
| Decide on contract length and any optional extensions | 0%
| Review final version prior to publication | 0%
Attachment 2 – How to Bid | Complete document | 0%
| Decide on evaluation criteria (Price and quality % weightings) | 0%
| Decide on quality questions to be answered by suppliers and scored in evaluation | 0%
| Review final version prior to publication | 0%
Pricing Matrix | Create Pricing Matrix for suppliers to submit their prices | 0%
| Review final version prior to publication | 0%
| 'Lock' cells and 'protect' Excel workbook prior to publication | 0%
Terms and Conditions | Download Terms and Conditions | 0% | They are found in the Documents section on the CCS RM6264 website. | RM6264 CCS webpage ADD LINK
| Decide which Terms and Conditions to use for this procurement | 0% | Use the Document Tracker in the next sheet.
| Update yellow bracketed areas - DPS Schedules | 0% | These are all mandatory Schedules
| Update yellow bracketed areas - DPS Joint Schedules | 0% | Some of these Schedules are optional
| Update yellow bracketed areas - DPS Order Schedules | 0% | Some of these Schedules are optional
Supplier List | Register to access DPS Marketplace system | 0% | Access the system as a buyer | Access the system
| Decide on most appropriate service and location filters for this procurement | 0%
| Run DPS filters and export supplier list (use within 2 working days) | 0%
Online procurement tool - Part 1 | Decide which online procurement tool to use | 0%
| (Optional) Register to access CCS's eSourcing procurement tool | 0%
| Finalise and gather all tender documentation, and name all documents accordingly | 0% | For example: Attachment 4, Attachment 5, Appendix 1
| Build procurement in online procurement tool | 0%
Capability Assessment (Optional) | Complete document with key requirements to refine shortlist | 0%
| Send Capability Assessment to supplier list via online procurement tool | 0% | See "Bid Pack Templates" on RM6264 CCS webpage | RM6264 CCS webpage ADD LINK
| Review submitted Capability Assessments and shortlist accordingly | 0%
Online procurement tool - Part 2 | Invite suppliers to tender via online procurement tool | 0%
| Respond to clarification questions via online procurement tool | 0%
| Decide on evaluation team (who will evaluate the tenders?) | 0% | At least 3 suitably experienced and qualified evaluators are usually chosen. Separate individual(s) should be used to evaluate price.
| Book time in evaluators' diaries for evaluating tenders and for moderation | 0%
Organise site visits (Optional) | Organise with suppliers when they can visit your premises in order to help them bid | 0% | Make sure you share the same information with all suppliers throughout this stage, to ensure competition remains fair.
Evaluate tender responses | Upon the tender response deadline, download tender responses from online procurement tool and send to evaluators | 0%
| Evaluate tender responses | 0%
| Moderate tender responses and decide on winning bid | 0%
Internal governance (If applicable) | Submit the decision to award contract for internal approval | 0%
| Receive and log approval | 0%
Outcome letters | Draft outcome letters to all suppliers that submitted a bid | 0% | Include constructive feedback to all suppliers who bid, including a full breakdown of their score, and a comparison to the score of the winning supplier. There are template outcome letters on the RM6264 CCS webpage. | RM6264 CCS webpage ADD LINK
| Send outcome letters to all suppliers | 0%
Supplier due diligence (if applicable) | Ask winning supplier for evidence of information mentioned in their bid | 0%
| Ask winning supplier for evidence of information provided to be appointed onto the cleaning DPS e.g. contract example, Cyber Essentials certificate, insurance | 0% | You can log-in to the DPS system and navigate to the supplier search you used for this procurement. Find the supplier(s) you wish to see further information for and click on ‘Request evidence’. The suppliers will then be sent a notification and will give you access to see the evidence. | DPS system
| Complete supplier due diligence checks e.g. financial, references | 0%
| Review evidence and confirm decision to award contract to winning supplier | 0%
Order Schedules | Complete/amend Order Schedules | 0% | Use the Document Tracker in the next sheet to keep track.
Order Form | Confirm contract start date with supplier | 0%
| Complete DPS Schedule 6 - Order Form | 0%
| Sign Order Form (contract) with supplier | 0%
Inform CCS | Inform CCS of the contract award | 0% | Complete the Contract Award Notification letter on the RM6264 CCS website and send to info@crowncommercial.gov.uk : Contract name, supplier and buyer details, contract length (including any extensions), contract total value.
Find a Tender (if applicable) | Publish contract details on Contracts Finder/Find a Tender website | 0%
Implementation/Mobilisation | Manage implementation of the new service with the new and incumbent supplier | 0%
If you need any help or have any questions about the RM6264 Facilites Management and Workplace Services DPS, contact info@crowncommercial.gov.uk (Quote RM6264)

## Document Tracker
All documents can be found under the 'Documents' tab on the RM6264 web page: https://www.crowncommercial.gov.uk/agreements/RM6264
Document Title | Required? | Include? | Progress | Comments
Further Competition
Attachment 1 - About the Procurement | Yes | Yes | 0% | This document give suppliers the core information about your procurement.
Attachment 2 - How to Bid | Yes | Yes | 0% | This document informs suppliers how they should bid, including which online procurement tool you will use.
Attachment 3 - Requirements Specification | Yes | Yes | 0% | This is the main document that tells suppliers the who, what, where, when, why and how of the service that you require. It also can form part of your contract. Your Quality Questions will be based on the information provided in this document.
Attachment 4 - Core Terms & Schedules (including Order Form) | Yes | Yes | 0% | Once you have chosen and completed the relevant Ts&Cs listed below (DPS Schedules, Joint Schedules, Order Schedules) that apply to your procurement, save them all in a ZIP folder named "Attachment 4 - Core Terms & Schedules (including Order Form)".
Attachment 5 - Pricing Matrix | Yes | Yes | 0% | This is the spreadsheet that bidding suppliers will use to input their proposed prices. You can structure your pricing model however is best for your contract and may choose to use the template document or not.
Attachment 6 - TUPE Information | If applicable |  | 0% | Ask your existing service provider to complete this template. Applies to all procurements where there is an existing service provider delivering the current service.
Ts&Cs (DPS Schedules)
DPS Appointment Form v1 (Sample) | Mandatory | Yes | 100% | Example supplier Appointment Form.
DPS Core Terms v1 | Mandatory | Yes | 100% | CCS's core terms.
DPS Schedule 1 - Specification | Mandatory | Yes | 100% | The specification of the services that suppliers need to meet.
DPS Schedule 2 - DPS Application | Mandatory | Yes | 100% | The application questions that suppliers complete to join the RM6264 DPS.
DPS Schedule 3 - DPS Pricing | Mandatory | Yes | 100% | Details how DPS pricing works and the limits imposed on charges from suppliers.
DPS Schedule 4 - DPS Management | Mandatory | Yes | 100% | Details how the DPS is managed by CCS.
DPS Schedule 5 - Management Levy and Information | Mandatory | Yes | 100% | Details the Management Levy and information.
DPS Schedule 6 - Order Form Template and Order Schedules | Mandatory | Yes | 0% | This is the Order Contract - a key document. To be completed as much as possible pre-tender and finalised at contract award.
DPS Schedule 7 - Order Procedure | Mandatory | Yes | 0% | Input your award criteria in the annex - this should mirror the information in Attachment 2 - How to Bid.
DPS Schedule 8 - Self Audit Certificate | Mandatory | Yes | 100% | A form used by CCS to audit suppliers.
DPS Schedule 9 - Cyber Essentials Scheme | Mandatory | Yes | 100% | Details the requirements of suppliers to have a Cyber Essentials certificate.
Ts&Cs (Joint Schedules)
DPS Joint Schedule 1 - Definitions | Mandatory | Yes | 100% | Details the definitions of terms used in the Schedules.
DPS Joint Schedule 2 - Variation Form | Mandatory | Yes | 100% | If you or your supplier would like to change any Schedules during the contract, this is the document to complete - both parties need to agree.
DPS Joint Schedule 3 - Insurance Requirements | Mandatory | Yes | 100% | Details the minimum insurance requirements of suppliers.
DPS Joint Schedule 4 - Commercially Sensitive Information | Mandatory | Yes | 0% | To be completed after contract award.
DPS Joint Schedule 5 - Corporate Social Responsibility | Mandatory | Yes | 100% | Details the corporate social responsibilities of suppliers.
DPS Joint Schedule 6 - Key Subcontractors | If applicable |  | 100% | Details the process the supplier shall follow to change sub-contractors during the contract.
DPS Joint Schedule 7 - Financial Difficulties | If applicable |  | 100% | Details what shall happen if the supplier's financial risk score changes or if the supplier goes into financial distress.
DPS Joint Schedule 8 - Guarantee | If applicable |  | 0% | To be completed after contract award if applicable.
DPS Joint Schedule 9 - Minimum Standards of Reliability | If applicable |  | 100% | Outlines that suppliers must show that they meet certain minimum standards of reliability if the anticipated contract value is over £20 million (excluding VAT).
DPS Joint Schedule 10 - Rectification Plan | Mandatory | Yes | 100% | During the contract, this form can be completed if the supplier encounters an issue that needs formally rectifying.
DPS Joint Schedule 11 - Processing Data | Mandatory | Yes | 0% | To be completed as much as possible pre-tender and finalised at contract award.
DPS Joint Schedule 12 - Supply Chain Visibility | Mandatory | Yes | 100% | Details the responsibilities of the supplier to ensure supply chain visibility.
Ts&Cs (Order Schedules)
DPS Order Schedule 1 - Transparency Reports | Mandatory | Yes | 0% | Applies to all Central Government Departments, their Executive Agencies and Non Departmental Public Bodies. It concerns the publication of procurement and contracts information to be disclosed to the public.
DPS Order Schedule 2 - Staff Transfer | Mandatory | Yes | 0% | Concerns TUPE and staff transferring into and out of the contract.
DPS Order Schedule 3 - Continuous Improvement | Mandatory | Yes | 100% | Details the supplier's responsibilities regarding continuous improvement.
DPS Order Schedule 4 - Order Tender | If applicable |  | 0% | To complete after contract award. Copy the winning supplier's tender response into this Schedule.
DPS Order Schedule 5 - Pricing Details | If applicable |  | 0% | To complete after contract award. Copy the winning supplier's Pricing Matrix into this Schedule.
DPS Order Schedule 7 - Key Supplier Staff | If applicable |  | 0% | To be completed after contract award. Supplier to detail the key members of its staff to work on the contract.
DPS Order Schedule 8 - Business Continuity and Disaster Recovery | If applicable |  | 100% | Applies if you require the supplier to have Business Continuity and Disaster Recovery plans.
DPS Order Schedule 9 - Security | If applicable |  | 0% | Choose the level of security requirements for the contract.
DPS Order Schedule 10 - Exit Management | If applicable |  | 0% | Details the supplier's exit management responsibilities.
DPS Order Schedule 11 - Installation Works | If applicable |  | 100% | Applies if you require the supplier to install anything during the contract.
DPS Order Schedule 12 - Clustering | If applicable |  | 0% | Applies if you are procuring services as part of a cluster of organisations.
DPS Order Schedule 13 - Implementation Plan and Testing | If applicable |  | 0% | Provides details around the implementation/mobilisation of the contract.
DPS Order Schedule 14 - Service Levels | If applicable |  | 0% | Contains your chosen KPIs/service levels for this contract. If you detail your Service Levels in the Requirements Specification, duplicate them here. If you only include your Service Levels in this Schedule, refer to this Schedule in your Requirements Specification.
DPS Order Schedule 15 - Order Contract Management | If applicable |  | 0% | Provides details around contract management responsibilities.
DPS Order Schedule 16 - Benchmarking | If applicable |  | 100% | Applies if you require the supplier to cooperate in a benchmarking exercise no less than every 12 months, to determine if the contract provides good value. Benchmarking exercise are at the cost of the Buyer.
DPS Order Schedule 17 - MoD Terms | If applicable |  | 0% | Applies to Ministry of Defence (MoD) procurements only.
DPS Order Schedule 18 - Background Checks | If applicable |  | 0% | Details the Relevant Convictions that shall exclude people from working on the contract.
DPS Order Schedule 19 - Scottish Law | If applicable |  | 0% | Applies if you wish the contract to be governed under Scottish law.
DPS Order Schedule 20 - Specification | If applicable |  | 0% | Copy over your "Attachment 3 - Requirements Specification" (once it is finalised), so that it forms part of the contract.
DPS Order Schedule 21 - Northern Ireland Law | If applicable |  | 100% | Applies if you wish the contract to be governed under Northern Ireland law.
DPS Order Schedule 22 - Lease Terms | If applicable |  | 0% | Applies if you are going to be leasing equipment.
DPS Order Schedule 23 - HMRC | If applicable |  | 0% | This schedule contains additional terms required by HMRC buyers
DPS Order Schedule 24 - Supplier Furnished Terms | If applicable |  | 0% | This schedule may be used where buyers have specific technology requirements.
DPS Order Schedule 25 - Billable Works and Projects | If applicable |  | 0% | This schedule outlines the Billable Works process
DPS Order Schedule 26 - Buyer Remedies for Default and Step in Rights | If applicable |  | 0% | This schedule is used if the supplier commits any default on their Order Contract, and gives the buyer options for remedies.
DPS Order Schedule 27 - Construction Contracts | If applicable |  | 0% | Sets out how a supplier can access Government Frameworks and specific terms relating to construction contracts where construction projects may be a part of order contract