## 2025
January 2025 Competition (06/12/2023 - 01/02/2025)
Action	Completion Date	Action Owner		Key
Customer to submit site addition template and pre-populated call-off to CCS	06/12/2024	Customer		Commercial Agreement Manager (CAM)
Aggregate customer site lists into master document (per lot)	09/12/2024 - 10/12/2024	CAM		Procurement Operations (PO)
Prepare Inviatation to Tender bid packs	09/12/2024 - 24/12/2024	CAM/ PO
Publish Inviatation to Tender (1 per lot)	03/01/2025	PO
Respond to supplier clarifications	15/01/2025	CAM/ PO
Invitation to Tender Closes	17/01/2025	PO
Evaluation of responses	20/01/2025 - 21/01/2025	CAM/ PO
Issue award notification to suppliers	23/01/2025	PO
Create customer award templates (add price to customer site lists)	20/01/2025 - 24/01/2025	CAM
Issue award notification to customers	24/01/2025 - 31/01/2025	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/02/2025 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/02/2025 + 90 working days	Supplier
Contract Commences	01/02/2025 + 90 working days	Customer

April 2025 Competition (07/03/2025 - 01/05/2025)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	07/03/2025	Customer
Aggregate customer site lists into master document (per lot)	10/03/2025 - 11/03/2025	CAM
Prepare Inviatation to Tender bid packs	10/03/2025 - 24/03/2025	CAM/ PO
Publish Inviatation to Tender (1 per lot)	01/04/2025	PO
Respond to supplier clarifications	11/04/2025	CAM/ PO
Invitation to Tender Closes	15/04/2025	PO
Evaluation of responses	17/04/2025 - 18/04/2025	CAM/ PO
Issue award notification to suppliers	22/04/2025	PO
Create customer award templates (add price to customer site lists)	17/04/2025 - 25/04/2025	CAM
Issue award notification to customers	25/04/2025 - 30/04/2025	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/05/2025 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/05/2025 + 90 working days	Supplier
Contract Commences	01/05/2025 + 90 working days	Customer

July 2025 Competition (06/06/2025 - 01/08/2025)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	06/06/2025	Customer
Aggregate customer site lists into master document (per lot)	09/06/2025 - 10/06/2025	CAM
Prepare Inviatation to Tender bid packs	09/06/2025 - 25/06/2025	CAM/ PO
Publish Inviatation to Tender (1 per lot)	01/07/2025	PO
Respond to supplier clarifications	11/07/2025	CAM/ PO
Invitation to Tender Closes	15/07/2025	PO
Evaluation of responses	17/07/2025 - 18/07/2025	CAM/ PO
Issue award notification to suppliers	22/07/2025	PO
Create customer award templates (add price to customer site lists)	17/07/2025 - 24/07/2025	CAM
Issue award notification to customers	24/07/2025 - 31/07/2025	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/08/2025 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/08/2025 + 90 working days	Supplier
Contract Commences	01/08/2025 + 90 working days	Customer

October 2025 Competition (05/09/2025 - 01/11/2025)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	05/09/2025	Customer
Aggregate customer site lists into master document (per lot)	08/09/2025 - 09/09/2025	CAM
Prepare Inviatation to Tender bid packs	08/09/2025 - 26/09/2025	CAM/ PO
Publish Inviatation to Tender (1 per lot)	01/10/2025	PO
Respond to supplier clarifications	13/10/2025	CAM/ PO
Invitation to Tender Closes	15/10/2025	PO
Evaluation of responses	17/10/2025 - 20/10/2025	CAM/ PO
Issue award notification to suppliers	22/10/2025	PO
Create customer award templates (add price to customer site lists)	17/10/2025 - 24/10/2025	CAM
Issue award notification to customers	24/10/2025 - 31/10/2025	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/11/2025 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/11/2025 + 90 working days	Supplier
Contract Commences	01/11/2025 + 90 working days	Customer

## 2026
January 2026 Competition (05/12/2025 - 02/02/2026)
Action	Completion Date	Action Owner		Key
Customer to submit site addition template and pre-populated call-off to CCS	05/12/2025	Customer		Commercial Agreement Manager (CAM)
Aggregate customer site lists into master document (per lot)	08/12/2025 - 10/12/2025	CAM		Procurement Operations (PO)
Prepare Inviatation to Tender bid packs	08/12/2025 - 27/12/2025	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	02/01/2026	PO
Respond to supplier clarifications (Subject to change)	15/01/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	16/01/2026	PO
Evaluation of responses (Subject to change)	19/01/2026 - 20/01/2026	CAM/ PO
Issue award notification to suppliers	21/01/2026	PO
Create customer award templates (add price to customer site lists)	20/01/2026 - 23/01/2026	CAM
Issue award notification to customers	26/01/2026 - 31/01/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	02/02/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	02/02/2026 + 90 working days	Supplier
Contract Commences	02/02/2026 + 90 working days	Customer
	02/02/2026 + 90 working days
April 2026 Competition (07/03/2026 - 01/05/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	06/03/2026	Customer
Aggregate customer site lists into master document (per lot)	09/03/2026 - 11/03/2026	CAM
Prepare Inviatation to Tender bid packs	09/03/2026 - 27/03/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/04/2026	PO
Respond to supplier clarifications (Subject to change)	10/04/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/04/2026	PO
Evaluation of responses (Subject to change)	17/04/2026 - 20/04/2026	CAM/ PO
Issue award notification to suppliers	21/04/2026	PO
Create customer award templates (add price to customer site lists)	17/04/2026 - 24/04/2026	CAM
Issue award notification to customers	24/04/2026 - 29/04/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/05/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/05/2026 + 90 working days	Supplier
Contract Commences	01/05/2026 + 90 working days	Customer

July 2026 Competition (06/06/2026 - 01/08/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	05/06/2026	Customer
Aggregate customer site lists into master document (per lot)	08/06/2026 - 10/06/2026	CAM
Prepare Inviatation to Tender bid packs	08/06/2026 - 26/06/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/07/2026	PO
Respond to supplier clarifications (Subject to change)	10/07/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/07/2026	PO
Evaluation of responses (Subject to change)	17/07/2026 - 20/07/2026	CAM/ PO
Issue award notification to suppliers	21/07/2026	PO
Create customer award templates (add price to customer site lists)	17/07/2026 - 24/07/2026	CAM
Issue award notification to customers	24/07/2026 - 31/07/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/08/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/08/2026 + 90 working days	Supplier
Contract Commences	01/08/2026 + 90 working days	Customer

October 2026 Competition (05/09/2026 - 01/11/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	04/09/2026	Customer
Aggregate customer site lists into master document (per lot)	07/09/2026 - 09/09/2026	CAM
Prepare Inviatation to Tender bid packs	07/09/2026 - 25/09/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/10/2026	PO
Respond to supplier clarifications (Subject to change)	13/10/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/10/2026	PO
Evaluation of responses (Subject to change)	16/10/2026 - 20/10/2026	CAM/ PO
Issue award notification to suppliers	22/10/2026	PO
Create customer award templates (add price to customer site lists)	16/10/2026 - 23/10/2026	CAM
Issue award notification to customers	23/10/2026 - 30/10/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/11/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/11/2026 + 90 working days	Supplier
Contract Commences	01/11/2026 + 90 working days	Customer