Special Call-Off Schedule 13A (Implementation)
[Buyer Guidance: This Special Call-Off Schedule can only be used where Special Call-Off Schedule 13B (Testing) is also being used. Refer to the Framework Special Terms within the Framework Award Form and Order Form for additional terms which relate to this Special Call-Off Schedule.]

1. Definitions
  1. In this Schedule, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):
"Allowable Price"	in relation to the Retained Deliverables relating to a CPP Milestone, if any, an amount determined in accordance with the formula: / A – B / where: / A is an amount equal to the Costs incurred by the Supplier in providing or developing the relevant Retained Deliverables as reflected in the Financial Model together with an amount equal to the Anticipated Contract Life Profit Margin thereon; and / B is an amount equal to the Allowable Price Adjustment relating to the relevant Retained Deliverables, if any, or if there is no such Allowable Price Adjustment, zero, / provided that the Allowable Price for any Retained Deliverables shall in no circumstances exceed the aggregate amount of the Milestone Payments paid to the Supplier in respect of the Milestones (or in the case of Partial Termination, the Milestones for the parts of the Services terminated) relating to that CPP Milestone;
“Delay Deduction Period”	the period of one hundred (100) days commencing on the relevant Milestone Date;
“Detailed Implementation Plan”	the plan developed and revised from time to time in accordance with Paragraphs ‎3 and ‎4 of this Schedule;
“Milestone Adjustment Payment Amount”	in respect of each CPP Milestone that is the subject of a Milestone Adjustment Payment Notice, an amount determined in accordance with the formula: / A – B / where: / (a) A is an amount equal to the aggregate sum of all Milestone Payments paid to the Supplier in respect of the Milestones (or in the case of a partial termination, the Milestones for the parts of the Deliverables terminated) relating to that CPP Milestone; and / (b) B is an amount equal to the aggregate Allowable Price for the Retained Deliverables relating to that CPP Milestone or, if there are no such Retained Deliverables, zero;
“Milestone Adjustment Payment Notice”	has the meaning given in Paragraph ‎10.1;
“Milestone Date”	the target date set out against the relevant Milestone in the Implementation Plan by which the Milestone must be Achieved;
“Milestone Achievement Certificate”	the certificate to be granted by the Buyer when the Supplier has Achieved a Milestone, which shall be in substantially the same form as that set out in Annex 3 of Special Call-Off Schedule 13B (Testing);
“Milestone Retention”	has the meaning given in Paragraph ‎8;
“Non-retained Deliverables”	in relation to a CPP Milestone Payment notice and each CPP Milestone the subject of that CPP Milestone Payment Notice, Deliverables provided to the Authority which relate to the relevant CPP Milestone(s) and which are not Retained Deliverables; and
“Outline Implementation Plan”	the outline plan set out at Annex 1 of this Schedule.

1. Introduction
  1. This Schedule:
    1. defines the process for the preparation and implementation of the Outline Implementation Plan and the Detailed Implementation Plan; and
    2. identifies the Milestones (and associated Deliverable Items) including the Milestones which trigger payment to the Supplier of the applicable Milestone Payments following the issue of the applicable Milestone Achievement Certificate.
2. Outline Implementation Plan
  1. The Outline Implementation Plan is set out in Annex 1.
  2. All changes to the Outline Implementation Plan shall be subject to the Variation Procedure provided that the Supplier shall not attempt to postpone any of the Milestones using the Variation Procedure or otherwise (except in accordance with Clause 5 (The Buyer’s obligations to the Supplier) of the General Terms). [Buyer Guidance: Framework Special Term 7 (Authority cause) should be considered]
  3. The Supplier shall note that it is incumbent upon them to understand the lead-in period for security clearances and ensure that all Supplier Staff have the necessary security clearance in place before the Call-Off Start Date. The Supplier shall ensure that this is reflected in the Outline Implementation Plan.
  4. The Supplier shall ensure that all Supplier Staff do not access the Buyer's IT systems, or any IT systems linked to the Buyer, unless they have satisfied the Buyer's security requirements.
  5. The Supplier shall be responsible for providing all necessary information to the Buyer to facilitate security clearances for Supplier Staff in accordance with the Buyer's requirements.
  6. The Supplier shall provide the names of all Supplier Staff and inform the Buyer of any alterations and additions as they take place throughout the Call-Off Contract Period.
  7. The Supplier shall ensure that all Supplier Staff requiring access to the Buyer Premises have the appropriate security clearance. It is the Supplier's responsibility to establish whether or not the level of clearance will be sufficient for access. Unless prior approval has been received from the Buyer, the Supplier shall be responsible for meeting the costs associated with the provision of security cleared escort services.
  8. If a property requires Supplier Staff to be accompanied by the Buyer’s Authorised Representative, the Buyer must be given reasonable notice of such a requirement, except in the case of emergency access.
3. Approval of the Detailed Implementation Plan
  1. The Supplier shall submit a draft of the Detailed Implementation Plan to the Buyer for approval within [20] Working Days [Buyer Guidance: Buyer to determine an appropriate duration], of the Call-Off Contract Start Date.
  2. The Supplier shall ensure that the draft Detailed Implementation Plan:
    1. incorporates all of the Milestones and Milestone Dates set out in the Outline Implementation Plan;
    2. includes (as a minimum) the Supplier’s proposed timescales in respect of the following for each of the Milestones:
1. the completion of each design document;
2. the completion of the build phase;
3. the completion of any Testing to be undertaken in accordance with Special Call-Off Schedule 13B (Testing); and
4. training and roll-out activities;
    1. clearly outlines all the steps required to implement the Milestones to be achieved in the next [X] months [Buyer Guidance: Buyer to determine an appropriate duration], together with a high level plan for the rest of the programme, in conformity with the Buyer Requirements;
    2. clearly outlines the required roles and responsibilities of both Parties, including staffing requirements; and
    3. is produced using a software tool as specified, or agreed by the Buyer.
  2. Prior to the submission of the draft Detailed Implementation Plan to the Buyer in accordance with Paragraph 4.1, the Buyer shall have the right:
    1. to review any documentation produced by the Supplier in relation to the development of the Detailed Implementation Plan, including:
1. details of the Supplier’s intended approach to the Detailed Implementation Plan and its development;
2. copies of any drafts of the Detailed Implementation Plan produced by the Supplier; and
3. any other work in progress in relation to the Detailed Implementation Plan; and
    1. to require the Supplier to include any reasonable changes or provisions in the Detailed Implementation Plan.
  2. Following receipt of the draft Detailed Implementation Plan from the Supplier, the Buyer shall:
    1. review and comment on the draft Detailed Implementation Plan as soon as reasonably practicable; and
    2. notify the Supplier in writing that it approves or rejects the draft Detailed Implementation Plan no later than [20] Working Days [Buyer Guidance: Buyer to determine an appropriate duration], after the date on which the draft Detailed Implementation Plan is first delivered to the Buyer.
  3. If the Buyer rejects the draft Detailed Implementation Plan:
    1. the Buyer shall inform the Supplier in writing of its reasons for its rejection; and
    2. the Supplier shall then revise the draft Detailed Implementation Plan (taking reasonable account of the Buyer’s comments) and shall re-submit a revised draft Detailed Implementation Plan to the Buyer for the Buyer’s approval within [20] Working Days [Buyer Guidance: Buyer to determine an appropriate duration], of the date of the Buyer’s notice of rejection. The provisions of Paragraph 4.4 and this Paragraph 4.5 shall apply again to any resubmitted draft Detailed Implementation Plan, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.
  4. If the Buyer approves the draft Detailed Implementation Plan, it shall replace the Outline Implementation Plan from the date of the Buyer’s notice of approval.
2. Updates to and Maintenance of the Detailed Implementation Plan
  1. Following the approval of the Detailed Implementation Plan by the Buyer:

    1. the Supplier shall submit a revised Detailed Implementation Plan to the Buyer every 3 months starting 3 months from the Effective Date;
    2. without prejudice to Paragraph 5.1.1, the Buyer shall be entitled to request a revised Detailed Implementation Plan at any time by giving written notice to the Supplier and the Supplier shall submit a draft revised Detailed Implementation Plan to the Buyer within [20] Working Days [Buyer Guidance: Buyer to determine an appropriate duration], of receiving such a request from the Buyer (or such longer period as the Parties may agree provided that any failure to agree such longer period shall be referred to the Dispute Resolution Procedure);
    3. any revised Detailed Implementation Plan shall (subject to Paragraph 5.2) be submitted by the Supplier for approval in accordance with the procedure set out in Paragraph 4; and
    4. the Supplier’s performance against the Implementation Plan shall be monitored at meetings of the Operational Board (as defined in Call-Off Schedule 15 (Call-Off Contract Management). In preparation for such meetings, the current Detailed Implementation Plan shall be provided by the Supplier to the Buyer not less than 5 Working Days in advance of each meeting of the Operational Board.
  2. Save for any amendments which are of a type identified and notified by the Buyer (at the Buyer’s discretion) to the Supplier in writing as not requiring approval, any material amendments to the Detailed Implementation Plan shall be subject to the Variation Procedure provided that:
    1. any amendments to elements of the Detailed Implementation Plan which are based on the contents of the Outline Implementation Plan shall be deemed to be material amendments; and
in no circumstances shall the Supplier be entitled to alter or request an alteration to any Milestone Date except in accordance with Clause 5 (The Buyer’s obligations to the Supplier) of the General Terms. [Buyer Guidance: Framework Special Term 7 (Authority Cause) must be selected in the Call-Off Order Form or amend this Paragraph ‎5.2 accordingly]
  1. Any proposed amendments to the Detailed Implementation Plan shall not come into force until they have been approved in writing by the Buyer.
2. Delays
  1. The Supplier shall:
    1. comply with the Implementation Plan; and
    2. ensure that each Milestone is Achieved on or before its Milestone Date.
  2. If the Supplier becomes aware that there is, or there is reasonably likely to be, a Delay:
    1. it shall:
      1. notify the Buyer in accordance with Clause 11 (Rectifying Issues) of the General Terms; and
      2. comply with the Rectification Plan Process in order to address the impact of the Delay or anticipated Delay; and
      3. use all reasonable endeavours to eliminate or mitigate the consequences of any Delay or anticipated Delay; and
    1. if the Delay or anticipated Delay relates to a Key Milestone, the provisions of Paragraph 7 shall apply.
2. Delay Payments
  1. If a Key Milestone has not been Achieved by its relevant Milestone Date, the following provisions shall apply in relation to the payment of Delay Payments.
  2. Delay Payments shall be the Buyer's exclusive financial remedy for the Supplier’s failure to Achieve a Key Milestone by its Milestone Date except where:
    1. the Buyer is entitled to or does terminate this Contract pursuant to Clause 13.3 (When CCS or the Buyer can end a contract) of the General Terms; or
    2. the Delay exceeds the Delay Deduction Period.
  3. If a Key Milestone has not been Achieved on or before the relevant Milestone Date, the Supplier shall pay a Delay Payment to the Buyer in respect of that Key Milestone. Delay Payments shall accrue:
      1. at the daily rate (the “Delay Payment Rate”) determined in accordance with Paragraph 7.4;
      2. from (but excluding) the relevant Milestone Date to (and including) the earlier of:
        1. the date on which the Key Milestone is Achieved; and
        2. the expiry of the Delay Deduction Period; and
      3. on a daily basis, with any part day’s Delay counting as a day.
  4. Where a Delay Payment is payable in respect of a Key Milestone, the Delay Payment Rate shall be:
      1. where the Supplier has given the Buyer less than 3 months’ prior notice of the Delay, the amount set out in column 4 of Table 1 of Annex 2 for the Key Milestone;
      2. where the Supplier has given the Buyer between three (3) months’ and six (6) months’ prior notice of the Delay, the amount set out in column 5 of Table 1 of Annex 2 for the Key Milestone; or
      3. where the Supplier has given the Buyer more than 6 months’ prior notice of the Delay, the amount set out in column 6 of Table 1 of Annex 2 for the Key Milestone.
  5. The Supplier acknowledges and agrees that any Delay Payment is a price adjustment and not an estimate of the Loss that may be suffered by the Buyer as a result of the Supplier’s failure to Achieve the corresponding Milestone.
  6. The Delay Payment in respect of a Key Milestone shall be shown as a deduction from the amount due from the Buyer to the Supplier in the next invoice due to be issued by the Supplier after the date on which the relevant Key Milestone is Achieved or the expiry of the Delay Deduction Period (as the case may be). If the relevant Key Milestone is not Achieved by the expiry of the Delay Deduction Period and no invoice is due to be issued by the Supplier within 10 Working Days of expiry of the Delay Deduction Period, then the Supplier shall within 10 Working Days of expiry of the Delay Deduction Period:
      1. issue a credit note to the Buyer in respect of the total amount of the Delay Payment in respect of the Key Milestone (net of any payment made in respect of the Key Milestone pursuant to Paragraph 7.5), for use by the Buyer for accounting purposes; and
      2. pay to the Buyer as a debt a sum equal to the total amount of the Delay Payment in respect of the Key Milestone together with interest on such amount at the applicable rate under the Late Payment of Commercial Debts (Interest) Act 1998, accruing on a daily basis from (and including) the due date up to (but excluding) the date of actual payment, whether before or after judgment.
3. Milestone Retention
[Buyer guidance: where the Milestone Payment for a Milestone is determined by reference to the Outcome Based pricing mechanism set out in Annex 2 of Framework Schedule 3 (Framework Prices) the Buyer shall review and amend Paragraph ‎8.1 to correspond with the Outcome Based pricing mechanism. The Buyer should consider any other consequential amendments required in the Call-Off Contract.]
  1. The “Milestone Retention” for each Milestone shall be calculated as follows:
    1. where the Milestone Payment for the relevant Milestone is determined by reference to a Guaranteed Maximum Price with Target Cost pricing mechanism, 10% of the Target Price for the Milestone;
    2. where the Milestone Payment for the relevant Milestone is determined by reference to a Time and Materials, Fixed Price or Firm Price pricing mechanism, 10% of the Charges for that Milestone,
and, in the case of a Key Milestone, prior to deduction from the Milestone Payment of any Delay Payment attributable to that Key Milestone.
Release of Milestone Retentions
  1. On Achievement of a CPP Milestone relating to the Deliverables, the Supplier shall be entitled to invoice the Buyer for an amount equal to all Milestone Retentions that relate to Milestones identified in the “CPP Milestone Charge Number” column of Table 1 (or, in relation to Milestone Retentions in respect of Optional Deliverables, Table 2) of Annex 2 and corresponding CPP Milestone Charge Number identified in Table 2 of Annex 4 of Special Call-Off Schedule 13B (Testing) as being payable in respect of that CPP Milestone and have not been paid before such CPP Milestone. [Buyer Guidance: Refer to Framework Special Term 5 (Optional Deliverables) within the Framework Award Form and Order Form where Optional Deliverables form part of the scope of the Contract]

[OPTIONAL] [Payments for Delays due to Authority Cause [Buyer Guidance: This Paragraph is optional, if the Buyer wishes to use it then Framework Special Term 7 (Authority Cause) must be selected in the Call-Off Order Form]
[Buyer guidance: where the Milestone Payment for a Milestone is determined by reference to the Outcome Based pricing mechanism set out in Annex 2 of Framework Schedule 3 (Framework Prices) the Buyer shall review and amend Paragraph ‎9 to correspond with the Outcome Based pricing mechanism. The Buyer should consider any other consequential amendments required in the Call-Off Contract.]
  1. If the Supplier is entitled in accordance with Clause 5 (The Buyer’s obligations to the Supplier) of the General Terms to compensation for failure to Achieve a Milestone by its Milestone Date, then, subject always to Clause 14 (How much you can be held responsible for) of the General Terms, such compensation shall be determined in accordance with the following principles:
    1. the compensation shall reimburse the Supplier for additional Costs incurred by the Supplier that the Supplier:
1. can demonstrate it has incurred solely and directly as a result of the Authority Cause; and
2. is, has been, or will be unable to mitigate, having complied with its obligations under Clause 5 (The Buyer’s obligations to the Supplier) of the General Terms
together with an amount equal to the Anticipated Contract Life Profit Margin thereon;
    1. the compensation shall not operate so as to put the Supplier in a better position than it would have been in but for the occurrence of the Authority Cause;
    2. where the Milestone Payment for the relevant Milestone is to be calculated by reference to the Guaranteed Maximum Price with Target Cost pricing mechanism, then:
the Target Price for the Milestone shall be increased in accordance with the following formula:

where:
NTP	is the revised Target Price for the relevant Milestone;
TP	is the original Target Price for the relevant Milestone;
AC	is an amount equal to any additional Costs incurred by the Supplier in Achieving the Milestone to the extent that the Supplier can demonstrate that such additional Costs were caused by the Authority Cause; and
x	is the Supplier Profit Margin that the Supplier would have received in respect of the relevant Milestone on the basis of the unadjusted Target Cost and unadjusted Target Price for that Milestone, as set out in Table 4 of Part A of Call-Off Schedule 5 (Pricing Details), expressed as a decimal; and [Buyer Guidance: where using this Paragraph ‎9 the Buyer must also use the tables within Call-Off Schedule 5 (Pricing)]

the Guaranteed Maximum Price shall be increased to an amount equal to 110% of the Target Price as adjusted pursuant to Paragraph ‎‎9.1.1(a);
    1. where the relevant Milestone Payment is to be calculated based upon a Fixed Price or a Firm Price pricing mechanism, the compensation shall include such amount as is appropriate to maintain the Supplier Profit Margin set out in respect of the relevant Milestone in Table 5 or Table 6 of Part A of Call-Off Schedule 5 (Pricing Details); and [Buyer Guidance: where using this Paragraph‎ 9 the Buyer must also use the tables within Call-Off Schedule 5 (Pricing Details). Buyers should add further columns to the pricing tables as required to include Supplier Profit Margin]
    2. where the Milestone Payment includes any Charges which are capped, then to the extent that the compensation agreed pursuant to this 9.1.5 results in the Buyer paying additional Time and Materials Charges for resources or effort which the Supplier demonstrates are required as a result of the Authority Cause, such additional Time and Materials Charges shall be disregarded for the purposes of calculating the relevant cap.
  2. The Supplier shall provide the Buyer with any information the Buyer may require in order to assess the validity of the Supplier’s claim to compensation.
2. Termination
  1. If this Contract is terminated (in whole or in part) by the Buyer pursuant to Clause 13.3 (When CCS or the Buyer can end a contract) of the General Terms prior to Achievement of one or more CPP Milestones, the Buyer may at any time on or within 12 months of the issue of the relevant Termination Notice by issue to the Supplier of written notice (a “Milestone Adjustment Payment Notice”) require the Supplier to repay to the Buyer an amount equal to the aggregate Milestone Adjustment Payment Amounts in respect of each CPP Milestone to which the Milestone Adjustment Payment Notice relates.
  2. A Milestone Adjustment Payment Notice shall specify:
    1. each CPP Milestone to which it relates;
    2. in relation to each such CPP Milestone, each Deliverable Item relating to that CPP Milestone that the Buyer wishes to retain, if any (each such Deliverable Item being a “Retained Deliverable”); and
    3. those Retained Deliverables, if any, the Allowable Price for which the Buyer considers should be subject to deduction of an adjusting payment on the grounds that they do not or will not perform in all material respects in accordance with their specification (such adjusting payment being an “Allowable Price Adjustment”),
    4. and may form part of a Termination Notice.
  3. The Supplier shall within 10 Working Days of receipt of a Milestone Adjustment Payment Notice, in each case as applicable:
    1. notify the Buyer whether it agrees that the Retained Deliverables which the Buyer considers should be subject to an Allowable Price Adjustment as specified in the relevant Milestone Adjustment Payment Notice should be so subject; and
    2. in relation to each such Retained Deliverable that the Supplier agrees should be subject to an Allowable Price Adjustment, notify the Buyer of the Supplier’s proposed amount of the Allowable Price Adjustment and the basis for its approval;
    3. provide the Buyer with its calculation of the Milestone Adjustment Payment Amount in respect of each CPP Milestone the subject of the relevant Milestone Adjustment Payment Notice using its proposed Allowable Price Adjustment, including details of:
      1. all relevant Milestone Payments; and
      2. the Allowable Price of each Retained Deliverable; and
    4. provide the Buyer with such supporting information as the Buyer may require.
  4. If the Parties do not agree the calculation of a Milestone Adjustment Payment Amount within 20 Working Days of the Supplier’s receipt of the relevant Milestone Adjustment Payment Notice, either Party may refer the Dispute to the Dispute Resolution Procedure.
  5. If the Buyer issues a Milestone Adjustment Payment Notice pursuant to Paragraph 10.1:
    1. the Buyer shall:
      1. securely destroy or return to the Supplier all Non-retained Deliverables that are in tangible form; and
      2. ensure that all Non-retained Deliverables that are held in electronic, digital or other machine-readable form cease to be readily accessible (other than by the information technology staff of the Buyer) from any computer, word processor, voicemail system or any other device containing such all Non-retained Deliverables,
in each case as soon as reasonably practicable after repayment of the aggregate Milestone Adjustment Payment Amounts repayable pursuant to that Milestone Adjustment Payment Notice; and
all licences granted by the Supplier pursuant to Call-Off Schedule 1 (Intellectual Property Rights) in respect of Specially Written Software and New IPRs and any Supplier Software that is not COTS Software and/or Supplier Existing IPRs shall terminate upon such repayment to the extent that they relate to the Non-retained Deliverables.
1. Government Reviews
  1. The Supplier acknowledges that the Deliverables may be subject to Government review at key stages of the project. The Supplier shall cooperate with any bodies undertaking such review and shall allow for such reasonable assistance as may be required for this purpose within the Charges.
## Annex 1: Outline Implementation Plan
Milestone	Deliverables (bulleted list showing all Deliverable Items (and associated tasks) required for each Milestone)	Duration (Working Days)	Milestone Date	Buyer Responsibilities (if applicable)	Link to ATP/CPP	Delay Payment (Y or N)	Milestone retention
Concept Design	[Statement of Requirements System/Application Specifications Interface Specifications Systems Testing Strategy Implementation Strategy and Plan Risk and Issues Management Plan Outline Disaster Recovery Plan Project Schedule Service Management Plan]
Full Development	[Design Verification Reports Design Validation Reports Change Management Plan System/Application Implementation Plan Risk and Issues Management Project Schedule Service Management Plan]
System User Testing	System Test Report Risk and Issues Management Plan Project Schedule Service Management Plan Defects Log Final Inspection and Testing Report
User Readiness for Service	Training Plan Risk and Issues Log Implementation Plan Operations Plan Data Conversion & Cutover Plan Project Schedule Service Management Plan
Implementation	Implementation Plan Training Scripts
In Service Support	Post Implementation Report Data Conversion and Cut-Over Plan Service Delivery Reports Risk and Issues Log Service Management Plan Defects Log

## Annex 2: Charging Mechanism and Adjustments
Table 1: Milestone Payments and Delay Payments
Charge Number	Pricing Mechanism (FIX / FIRM / GMPTC / T&M / OUTCOME)	CPP Milestone Charge Number	Delay Payments (if Key Milestone) (£ per day)
			<3 months’ notice	3-6 months’ notice	>6 months’ notice
[Service Line 1]
[e.g. SL1M1]	[FIRM]	[e.g. S2M2]
[e.g. SL1M2]	[FIRM]	[e.g. S2M2]
[Service Line 2]
[e.g. SL2M1]	[FIRM]	[e.g. S2M2]
[e.g. SL2M2]	[FIRM]	[e.g. S2M2]
[Service Line [X] – insert further rows as necessary]
[etc.]

Table 2: Optional Deliverables Milestone Payments
Charge Number	Pricing Mechanism (FIX / FIRM / GMPTC / T&M / OUTCOME)	CPP Milestone Charge Number	Delay Payments (if Key Milestone) (£ per day)
[e.g. OMS1]	[FIRM]	[e.g. OMS2]
[e.g. OMS2]	[FIRM]	[e.g. OMS2]